## Questions for Katie
MODERN HOMESTEADING CONFERENCE 2026
Questions to Ask About Available Space & Infrastructure
• How much square footage can we dedicate to the photo experience area?
• Are there existing structures at Kootenai (barn, pavilion, open-air shelter)?
• Can we use fairground infrastructure (tie posts, fencing, existing shade)?
• Where can we stage/hold animals when not in rotation (backup area needed)?
• Is there water access near the photo area for animal comfort?
• Are there electrical outlets if we need them (for charging, lighting)?
• What's the ground surface (concrete, dirt, grass)? Any drainage concerns?
• Can fairgrounds provide any fencing/pens or do we need to bring everything?
• How many days/hours are we allocated? Is setup/breakdown day-before an option?
• Are there restrictions on vehicle access or animal setup near guest areas?

## Space Planning
SPACE REQUIREMENTS & LAYOUT
PHOTO STAGING AREA
Zone/Element | Width (ft) | Depth (ft) | Notes
Backdrop Wall | 15 | 1 | Where animals stand (branded overlay area)
Animal Approach Lane | 15 | 8 | Room for handler + animal to position
Guest Queue/Staging | 20 | 10 | Guests wait, then position for photo
Shade Coverage (total) |  |  | See Shading Sheet for calculation
Buffer Space (sides) | 5 |  | Safety clearance around animals
ESTIMATED TOTAL FOOTPRINT | ~50 ft | ~20 ft | ~1,000 sq ft minimum
ANIMAL HOLDING AREAS
Area | Size (ft) | Purpose | Notes
Primary Pen (morning animals) | 30x20 | Ponies/Donkeys staging | Shaded, tie posts
Backup Pen (animals not in rotation) | 30x20 | Clydesdales when not shooting | Access to water
Tie-Off Line (during shooting) | 20 | Handler holds 1 animal | Near photo backdrop

## Shading & Equipment
SHADING, PANELS & EQUIPMENT
WHAT YOU HAVE
Item | Qty | Size/Notes | Coverage (sq ft)
Shade Panels (you have) |  | Enter: How many? What size?
Portable Canopy |  | Enter: How many? Size (ft x ft)?
SHADING NEEDED
Area to Shade | ~1,000 | sq ft | Photo area + animal holding
Current Coverage | ? | sq ft | Based on panels you have (calculate above)
ADDITIONAL NEEDED |  | sq ft | Amount to purchase/rent
EQUIPMENT CHECKLIST
Equipment | Qty | Have? | Need to Buy/Rent?
Portable Shade Panels |  | Y/N
Canopy/Tent |  | Y/N
Fencing/Panels (for animal pens) |  | Y/N
Tie Posts/Hitching Posts |  | Y/N
Water Buckets & Supply |  | Y/N
Hay/Feed (for holding area) |  | Y/N
Extension Cords/Power setup |  | Y/N
Photo Backdrop Materials |  | Y/N
Branded Overlay Graphics |  | Y/N
Camera Equipment & Lighting |  | Y/N
Hand Tools (hammer, ties, etc) |  | Y/N
First Aid Kit (human + animal) |  | Y/N
Sun Protection (sunscreen, hats) |  | Y/N

## Timeline & Rotation
SETUP, TIMELINE & ANIMAL ROTATION
DAY BEFORE (or early morning)
Time | Task | Responsible | Notes
TBD | Transport animals to fairgrounds | You | Load trailers, setup holding pens
TBD | Install shade/panel structures | You + helper | Confirm fairground tie posts available
TBD | Set up photo backdrop & lighting | You | Test camera, overlay system
TBD | Water animals, set up feed | You | Ensure animals settled overnight
EVENT DAY SCHEDULE
Time | Activity | Animals | Notes
30 min before | Final setup, animal check | Primary group (ponies/donkeys) | Water, groom, ready for photos
START TIME | Photo area open, guests arrive | Rotate animals (30 min intervals?) | TBD based on conference schedule
MID-SHIFT | Animal rotation (swap ponies/donkeys for Clydesdales) | Switch groups | ~halfway through event
CLOSING TIME | Final guest photos, begin breakdown | Get animals settled | Load trailers, pack equipment

## Day-of Checklist
TRIBAL COWBOY — EVENT DAY CHECKLIST
BEFORE YOU LEAVE HOME
☐ | Animals fed, watered, ready to load
☐ | Trailers inspected (lights, hitch, safety)
☐ | Equipment loaded (shade, backdrop, tools)
☐ | Camera & overlay system tested
☐ | Food/water for animals during event
☐ | First aid kit packed
☐ | Weather check & contingency plan
B{row} | AT THE FAIRGROUNDS (Setup)
☐ | Confirm available space & tie posts
☐ | Set up shade structures
☐ | Position photo backdrop
☐ | Set up holding pens for inactive animals
☐ | Water stations ready
☐ | Test camera, lighting, overlay system
☐ | Animals settled in pens
B{row} | DURING THE EVENT
☐ | Monitor animal stress/comfort
☐ | Rotate animals on schedule
☐ | Keep water buckets full
☐ | Check guest photo overlays are loading
☐ | Maintain photo backdrop quality
☐ | Document the experience (photos for social)
B{row} | CLEANUP & BREAKDOWN
☐ | Animals checked (no injuries)
☐ | All equipment removed from fairgrounds
☐ | Trailers loaded, secured, departure confirmed
☐ | Post-event thank you to Katie
☐ | Document feedback & learnings